## Blank
3. Rural Blueprint Planning Grants
Project Title: Planning Project | [16 empty] | Grantee:
[5 empty] | FY 2013 |  |  |  | FY 2012/2014 | [11 empty] | FY 2014/2015 | [11 empty] | Deliverables
Task # | Task | Responsible Party | Costs | local Match | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
1 | Outreach and Education
1.1 | Internal education | Staff | 5000 | 1250 | [28 empty] | List of participants
1.2 | Public engagement | Staff | 5000 | 1250 | [28 empty] | Increase coordination with diverse groups/List of participants | bar: FY 2013 J to FY 2012/2014 N; FY 2012/2014 M to FY 2014/2015 A
2 | Data Collection and Development
2.1 | Evaluate existing data layers | Staff/Consultant | 20000 | 5000 | [28 empty] | GIS Data | bar: FY 2013 M to FY 2013 J
2.2 | Improve and create GIS layers | Staff/Consultant | 20000 | 5000 | [28 empty] | GIS Layers | bar: FY 2013 J to FY 2012/2014 A
3 | Establish Technical Advisory Committee
3.1 | Establish Committee | consultant | 10000 | 2500 | [28 empty] | List of participants and feed back from participants | bar: FY 2012/2014 S to FY 2012/2014 J
4 | Public Outreach and Involvement
4.1 | Develop public outreach involvement efforts | Staff | 20000 | 5000 | [28 empty] | List | bar: FY 2012/2014 O to FY 2012/2014 M
4.2 | Develop Public Involvement Plan | Staff | 30000 | 7500 | [28 empty] | Documented public involvement plan | bar: FY 2012/2014 O to FY 2012/2014 M
| Total |  | 110000 | 27500
This sample timeline is for illustrative purposes only. Your scope of work and timeline may include different tasks under different headings.
SAMPLE